## Sheet1
Actual Hours Spent
| Task | Estimate(hours) | Resources | Documenting | Coding | Total
Requirements analysis | Functional requirements gathering | 3
| Non-Functional requirements gathering | 3
Requirements specifications | Functional requirements specification | 6
| Non-Functional requirements specification | 6
Software design | Supporting diagrams | 5
| Database structure diagram | 3
Software coding | Create Database | 10
| Create Add, Update, Remove stored procedures | 8
| Create clothing interface | 30
| Create admin clothing interface | 20
| Create food interface | 30
| Create admin food interface | 20
| Create search functinality | 15
| Create browse functionality | 5
| Create filter functionality | 10
Create specials functionality
| Add test data | 5
| Add website images | 3
Software testing | Create test cases | 15
| Execute test cases | 5
| Update code based on test cases | 10
| End-to-End testing | 5
TOTAL |  | 217