## Sheet1
Actual Hours Spent
| Task | Estimate(hours) | Resources | Documenting | Coding | Total
Requirements analysis | Functional requirements gathering | 3 | 1 | 1 | 0 | 2
| Non-Functional requirements gathering | 3 | 0.5 | 0.5 | 0 | 1
Requirements specifications | Functional requirements specification | 6 | 2 | 3 | 0 | 5
| Non-Functional requirements specification | 6 | 0.5 | 2 | 0 | 2.5
Software design | Supporting diagrams | 5 | 2.5 | 3 | 0 | 5.5
| Database structure diagram | 3 | 4 | 0.5 | 2 | 6.5
Software coding | Create Database | 10 | 1 | 0 | 3 | 4
| Create Add, Update, Remove stored procedures | 8 | 0.5 | 0 | 4 | 4.5
| Create clothing interface | 30 |  |  |  | 0
| Create admin clothing interface | 20 |  |  |  | 0
| Create food interface | 30 |  |  |  | 0
| Create admin food interface | 20 |  |  |  | 0
| Create search functinality | 15 |  |  |  | 0
| Create browse functionality | 5 |  |  |  | 0
| Create filter functionality | 10 |  |  |  | 0
| Create specials functionality |  |  |  |  | 0
| Add test data | 5 |  |  |  | 0
| Download images | 4 | 2 | 0 | 0 | 2
| Add website images | 3 |  |  |  | 0
Software testing | Create test cases | 15 |  |  |  | 0
| Execute test cases | 5 |  |  |  | 0
| Update code based on test cases | 10 |  |  |  | 0
| End-to-End testing | 5 |  |  |  | 0
Software and tools gathering | Download tools | 5 | 3 | 0 | 0 | 3
TOTAL |  | 226